AZURE TO ON-PREMISES MIGRATION

VxRail VMware Infrastructure

Migration Plan, Architecture, Setup Guide & Runbook

| Document Version | 2.0 |
| --- | --- |
| Date | July 22, 2026 |
| Classification | Internal Use Only |
| Status | DRAFT — For Team Review |
| Infrastructure | 6-Node Dell VxRail HCI + VMware vSphere |

Please review and add comments/suggestions before the next team meeting.

# 1. Executive Summary

This document outlines the complete plan to migrate our multi-environment application platform from Microsoft Azure to our existing 6-node Dell VxRail HCI cluster running VMware vSphere. The migration covers Dev, QA, PreProd, and Prod environments across a 32-week timeline.

## 1.1 Why Migrate?

| Driver | Detail | Benefit |
| --- | --- | --- |
| Cost Savings | Azure spend ~$95,340/year → On-prem ongoing cost ~$30,000/year | ~$65,000/year saving |
| Data Sovereignty | Application data remains within our data centre, not Microsoft's cloud | Compliance benefit |
| Performance | Direct NVMe vSAN storage eliminates cloud network latency | 30-50% latency reduction |
| Control | Full access to hypervisor, OS, network, and storage layers | No vendor restrictions |
| Existing HW | 6-node VxRail already purchased and deployed — capacity available | No new HW purchase needed |

## 1.2 Key Facts

Source: Azure (AKS, Cosmos DB, PostgreSQL, ACR, Storage Account) — 4 environments

Target: VMware vSphere on Dell VxRail HCI (6 nodes, vSAN storage)

VM OS: Oracle Linux 9 (dnf/firewalld/SELinux — NOT Ubuntu)

Backup: Veeam Backup & Replication v12 (agentless via VMware APIs)

Timeline: 32 weeks total (includes procurement buffers, approval time, error recovery)

Phase 1: Dev + QA (Weeks 13-20)  |  Phase 2: PreProd + Prod (Weeks 21-30)

## 1.3 Migration Phases Overview

| Stage | Name | Activities |
| --- | --- | --- |
| STAGE 0 Weeks 1-4 | Discovery & Planning | Architecture review, hardware audit, procurement approval, change requests |
| STAGE 1 Weeks 5-8 | Hardware Delivery & Foundation | Hardware arrives, DNS/NTP/VPN/CA setup, Azure VPN tunnel |
| STAGE 2 Weeks 9-12 | Infrastructure Build | OL9 VMs, K8s cluster, vSAN, Harbor, ArgoCD, Veeam, Monitoring |
| STAGE 3 Weeks 13-20 | Phase 1: Dev + QA Migration | Databases migrated, apps deployed, 2 weeks validation per env |
| STAGE 4 Weeks 21-30 | Phase 2: PreProd + Prod | Live DB replication, maintenance window cutover, Azure decommission |
| STAGE 5 Weeks 31-32 | Hypercare & Handover | Monitor, fix issues, final documentation, team handover |

# 2. Architecture

## 2.1 Current Azure Architecture

Our current Azure setup consists of a Hub-and-Spoke network topology with four environment VNets, each running an identical stack: AKS (containers), Cosmos DB (MongoDB API), PostgreSQL, ACR (container images), and Azure Storage.

AZURE CLOUD — CURRENT STATE

═══════════════════════════════════════════════════════════════════════════════

Hub Subscription (Sub-AFRPS-AF-INT)

Hub VNet: 10.0.0.0/16

├── Azure VPN Gateway        — Site-to-site VPN / ExpressRoute

├── Azure Firewall           — Centralized egress + policy enforcement

├── Azure DNS Private Zones  — Internal service DNS resolution

└── Shared Services (ACR, Log Analytics, Key Vault, Monitor)

Spoke VNets (one per environment, peered to Hub):

┌────────────────┬────────────────┬─────────────────┬─────────────────┐

│   DEV VNet     │   QA VNet      │  PREPROD VNet   │   PROD VNet     │

│  10.10.0.0/16  │  10.20.0.0/16  │  10.30.0.0/16   │  10.40.0.0/16   │

├────────────────┼────────────────┼─────────────────┼─────────────────┤

│ AKS cluster    │ AKS cluster    │ AKS cluster     │ AKS cluster     │

│ 2-3 nodes      │ 2-3 nodes      │ 3-4 nodes       │ 4-6 nodes (HA)  │

├────────────────┼────────────────┼─────────────────┼─────────────────┤

│ Cosmos DB      │ Cosmos DB      │ Cosmos DB       │ Cosmos DB       │

│ (Mongo API)    │ (Mongo API)    │ (Mongo API)     │ (Multi-region)  │

├────────────────┼────────────────┼─────────────────┼─────────────────┤

│ PostgreSQL     │ PostgreSQL     │ PostgreSQL      │ PostgreSQL HA   │

│ Flexible Srv   │ Flexible Srv   │ Flexible Srv    │ (zone redundant)│

├────────────────┼────────────────┼─────────────────┼─────────────────┤

│ ACR (Std)      │ ACR (Std)      │ ACR (Premium)   │ ACR (Geo-rep)   │

├────────────────┼────────────────┼─────────────────┼─────────────────┤

│ Storage (LRS)  │ Storage (LRS)  │ Storage (ZRS)   │ Storage (RA-GRS)│

└────────────────┴────────────────┴─────────────────┴─────────────────┘

Monthly Azure Spend: ~$7,945/month    Annual: ~$95,340/year

## 2.2 What Each Azure Service Does

| Azure Service | Purpose | On-Prem Replacement |
| --- | --- | --- |
| AKS (Azure K8s Service) | Runs our containerised application workloads | Kubernetes on VxRail VMs |
| Azure Cosmos DB (Mongo API) | NoSQL document database — MongoDB-compatible API | MongoDB 7.0 ReplicaSet on OL9 VMs |
| Azure PostgreSQL | Relational database for structured app data | PostgreSQL 15 + Patroni HA on OL9 VMs |
| Azure Container Registry | Stores Docker images for app deployments | Harbor (self-hosted registry) on OL9 VM |
| Azure Storage Account | Object storage (blobs, files) — S3-like | MinIO on OL9 VM (S3-compatible) |
| Azure VPN Gateway | Secure connectivity between sites | IPsec VPN device (firewall) on-prem |
| Azure Firewall | Centralized network security policy | firewalld on each OL9 VM + DVS policies |
| Azure DNS Private Zones | Internal DNS resolution for services | BIND9 DNS server (OL9 VM, 10.0.1.5) |
| Azure Monitor + Log Analytics | Metrics and logs | Prometheus + Grafana + ELK Stack |
| Azure Key Vault | Secrets management | HashiCorp Vault (or K8s Secrets) |
| Azure Load Balancer | Traffic distribution to AKS pods | MetalLB (K8s) + keepalived VIP |

## 2.3 Current On-Premises Hardware (VxRail — What You Have Now)

YOUR DATA CENTRE — EXISTING VXRAIL CLUSTER

═══════════════════════════════════════════════════════════════════════════════

Dell VxRail HCI — 6 Nodes

┌──────────────────────────────────────────────────────────────────────┐

│   NODE 1        NODE 2        NODE 3        NODE 4        NODE 5/6   │

│  ┌────────┐   ┌────────┐   ┌────────┐   ┌────────┐   ┌──────────┐  │

│  │ ESXi   │   │ ESXi   │   │ ESXi   │   │ ESXi   │   │ ESXi x2  │  │

│  │ 8.x    │   │ 8.x    │   │ 8.x    │   │ 8.x    │   │ 8.x      │  │

│  │        │   │        │   │        │   │        │   │          │  │

│  │ CPU:   │   │ CPU:   │   │ CPU:   │   │ CPU:   │   │ CPU:     │  │

│  │ Dual   │   │ Dual   │   │ Dual   │   │ Dual   │   │ Dual     │  │

│  │ Xeon   │   │ Xeon   │   │ Xeon   │   │ Xeon   │   │ Xeon     │  │

│  │        │   │        │   │        │   │        │   │          │  │

│  │ RAM:   │   │ RAM:   │   │ RAM:   │   │ RAM:   │   │ RAM:     │  │

│  │ 256-   │   │ 256-   │   │ 256-   │   │ 256-   │   │ 256-     │  │

│  │ 512GB  │   │ 512GB  │   │ 512GB  │   │ 512GB  │   │ 512GB    │  │

│  │        │   │        │   │        │   │        │   │          │  │

│  │ NVMe:  │   │ NVMe:  │   │ NVMe:  │   │ NVMe:  │   │ NVMe:   │  │

│  │ 2-4TB  │   │ 2-4TB  │   │ 2-4TB  │   │ 2-4TB  │   │ 2-4TB   │  │

│  └────────┘   └────────┘   └────────┘   └────────┘   └──────────┘  │

│                                                                      │

│  Hypervisor: VMware ESXi 8.x (vSphere Enterprise Plus)              │

│  Management: VMware vCenter Server + VxRail Manager                 │

│  Storage:    vSAN (pooled NVMe across all 6 nodes)                  │

│  Network:    25 GbE LACP bonded (vmnic0 + vmnic1 per node)          │

│              DVS (Distributed Virtual Switch) — managed by vCenter  │

└──────────────────────────────────────────────────────────────────────┘

Aggregate Cluster Resources:

├── Total vCPU cores:     ~192-288 physical cores

├── Total RAM:            ~1.5-3 TB

├── Total vSAN raw:       ~12-24 TB NVMe

├── Usable vSAN (FTT=1):  ~6-12 TB (50% after RAID-1 protection)

└── Network:              25 GbE per node, ToR switches required

Running Today:

├── vCenter Server (management)

├── VxRail Manager (Dell lifecycle + health)

└── [Your existing workloads — do not disrupt these]

## 2.4 Target On-Premises Architecture (After Migration)

After migration, all four environments run on the VxRail cluster as OL9 VMs organised by VLAN and managed by Kubernetes namespaces.

TARGET ON-PREMISES ARCHITECTURE — VXRAIL VMWARE

═══════════════════════════════════════════════════════════════════════════════

Physical Layer (Dell VxRail — existing)

6x ESXi hosts  →  vCenter manages them as one cluster

vSAN pools NVMe disks across all 6 nodes into one shared datastore

VLAN / Network Segmentation (DVS Port Groups):

VLAN 10  —  PG-Management   (10.0.1.0/24)  — vCenter, DNS, Veeam, jump host

VLAN 20  —  PG-K8s-Nodes   (10.0.3-4.0/24) — K8s masters + workers

VLAN 30  —  PG-Databases   (10.0.5.0/24)   — PostgreSQL, MongoDB

VLAN 40  —  PG-Services    (10.0.6.0/24)   — Harbor, MinIO, monitoring

VLAN 80  —  vSAN traffic   (pre-configured by VxRail)

VLAN 90  —  vMotion         (pre-configured by VxRail)

VM Layer (Oracle Linux 9 — all 27 VMs):

MANAGEMENT (VLAN 10):

┌──────────────────────────────────────────────────────────────────┐

│  mgmt-jump-01 (10.0.1.20)   — Jump host: admin access, tools    │

│  mgmt-dns-01  (10.0.1.5)    — BIND9 internal DNS                │

│  mgmt-vbr-01  (10.0.1.40)   — Veeam B&R v12 (Windows 2022)     │

└──────────────────────────────────────────────────────────────────┘

KUBERNETES CONTROL PLANE (VLAN 20):

┌──────────────────────────────────────────────────────────────────┐

│  k8s-master-1 (10.0.3.11)  ─┐                                   │

│  k8s-master-2 (10.0.3.12)  ─┤─ HA API Server, etcd cluster      │

│  k8s-master-3 (10.0.3.13)  ─┘                                   │

│  API VIP:     (10.0.3.100) — keepalived + HAProxy (floats)      │

└──────────────────────────────────────────────────────────────────┘

KUBERNETES WORKERS (VLAN 20):

┌──────────────────────────────────────────────────────────────────┐

│  k8s-worker-1 (10.0.4.21)  ─┐  Dev + QA workloads              │

│  k8s-worker-2 (10.0.4.22)  ─┘  (K8s namespace separation)      │

│  k8s-worker-3 (10.0.4.23)  ─┐  PreProd workloads               │

│  k8s-worker-4 (10.0.4.24)  ─┘                                   │

│  k8s-worker-5 (10.0.4.25)  ─┐  Prod workloads (NoSchedule      │

│  k8s-worker-6 (10.0.4.26)  ─┘   taint — dedicated for Prod)    │

│  MetalLB Pool: 10.0.4.200-220 (LoadBalancer external IPs)       │

└──────────────────────────────────────────────────────────────────┘

DATABASES (VLAN 30):

┌──────────────────────────────────────────────────────────────────┐

│  pg-dev-01    (10.0.5.11)  PostgreSQL 15 — Dev                   │

│  pg-qa-01     (10.0.5.12)  PostgreSQL 15 — QA                    │

│  pg-preprod-01(10.0.5.13)  PostgreSQL 15 — PreProd               │

│  pg-prod-01   (10.0.5.21)  ─┐ PostgreSQL 15 — Prod HA           │

│  pg-prod-02   (10.0.5.22)  ─┤ (Patroni replication)             │

│  pg-prod-03   (10.0.5.23)  ─┘                                    │

│  mongo-dev-01 (10.0.5.14)  MongoDB 7.0 — Dev                     │

│  mongo-qa-01  (10.0.5.15)  MongoDB 7.0 — QA                      │

│  mongo-prod-01(10.0.5.24)  ─┐ MongoDB 7.0 — Prod ReplicaSet     │

│  mongo-prod-02(10.0.5.25)  ─┤                                    │

│  mongo-prod-03(10.0.5.26)  ─┘                                    │

└──────────────────────────────────────────────────────────────────┘

SHARED SERVICES (VLAN 40):

┌──────────────────────────────────────────────────────────────────┐

│  svc-harbor-01 (10.0.6.11) — Container Registry (replaces ACR)  │

│  svc-minio-01  (10.0.6.12) — Object Storage (replaces Azure Blob)│

│  svc-mon-01    (10.0.6.13) — Prometheus + Grafana + ELK         │

└──────────────────────────────────────────────────────────────────┘

KUBERNETES PLATFORM:

K8s version:   1.29

CNI:           Calico v3.27 (network policies)

LB:            MetalLB v0.14.8 (L2 ARP mode)

Storage CSI:   vSphere CSI v3.3.0 (PVs backed by vSAN)

Ingress:       Nginx Ingress Controller

GitOps:        ArgoCD (pulls from Git, deploys to K8s)

Namespaces:    dev / qa / preprod / prod (one per environment)

StorageClasses:

vsan-dev-qa      — FTT=0 (no redundancy — saves space in non-prod)

vsan-production  — FTT=1 RAID-1 (mirrored — for Prod)

vsan-databases   — RAID-5 (erasure coding — efficient for DB files)

# 3. Procurement & What We Already Have

## 3.1 What VxRail Already Provides

| Item | What It Is | Status |
| --- | --- | --- |
| ESXi hypervisor (6 nodes) | VMware ESXi 8.x | Included with VxRail |
| Compute | Dual Xeon CPUs + 256-512 GB RAM per node | Included with VxRail |
| vSAN Storage | NVMe pooled across all 6 nodes | Included with VxRail |
| vCenter Server | Central management UI for all VMs | Included with VxRail |
| VxRail Manager | Dell lifecycle, firmware, health dashboard | Included with VxRail |
| vSphere Enterprise Plus licence | Full vSphere feature set including DVS, DRS, HA | Bundled |
| vSAN licence | vSAN storage management | Bundled |
| 25 GbE NICs | 2x 25 GbE per node (LACP bonded) | Included with hardware |

## 3.2 What We Need to Procure

| Item | Description | Est. Cost | Lead Time | Why Needed |
| --- | --- | --- | --- | --- |
| ToR Switches (2x redundant) | Dell S5248F-ON (48x25GbE) or Cisco 9300 | $16,000-36,000 | 8-12 weeks | VLAN trunking for DVS port groups |
| Azure VPN Gateway | VpnGw1 SKU for data transfer during migration | $150-500/month | 1-3 days | Cancel after migration done |
| NAS for external backup | Synology DS1823xs+ (20-30 TB usable) | $5,000-8,000 | 2-4 weeks | Backups must NOT be on vSAN |
| Wildcard TLS cert | *.internal.company.com | $100-600/year | 1-3 days | Optional — internal CA is free |
| VPN appliance | FortiGate 60F or use existing firewall | $1,000-5,000 | 1-2 weeks | If no IPsec VPN device exists |

NOTE:  ORDER SWITCHES AND NAS IMMEDIATELY (Week 1) — 8-12 week hardware lead time. Everything else depends on hardware arriving.

## 3.3 Software (All Free / Open Source)

| Tool | Purpose | Cost |
| --- | --- | --- |
| Kubernetes 1.29 | Container orchestration (replaces AKS) | Free |
| Calico v3.27 | K8s network plugin + NetworkPolicy | Free |
| MetalLB v0.14.8 | LoadBalancer IPs for K8s services | Free |
| Harbor | Container registry (replaces ACR) | Free |
| ArgoCD | GitOps deployment (replaces Azure DevOps Pipelines) | Free |
| Prometheus + Grafana | Monitoring + dashboards (replaces Azure Monitor) | Free |
| MinIO | Object storage S3-compatible (replaces Azure Blob) | Free |
| PostgreSQL 15 | Relational database (replaces Azure PostgreSQL) | Free |
| MongoDB 7.0 Community | NoSQL database (replaces Cosmos DB) | Free |
| Patroni | PostgreSQL HA (automatic failover) | Free |
| Veeam B&R v12 | VM backup via VMware APIs | Licence required — check if owned |
| vSphere CSI v3.3.0 | Storage driver for K8s on vSphere | Free (VMware OSS) |
| govc | vSphere CLI for scripting | Free |
| Ansible | Configuration management / automation | Free |
| step-ca | Internal Certificate Authority | Free |

# 4. VMware / vSphere Initial Setup

This section covers everything that must be done in vCenter and on the VxRail cluster BEFORE any VMs are created or migration starts.

## 4.1 Step-by-Step VMware Setup Flow

VMWARE SETUP ORDER (must follow this sequence)

═══════════════════════════════════════════════════════════

Step 1:  Verify VxRail health (VxRail Manager + vCenter)

└── All 6 nodes green, vSAN healthy, no pending alerts

Step 2:  Configure physical switch VLANs (ToR switch)

└── Trunk VLANs 10,20,30,40,80,90 on all VxRail uplinks

Step 3:  Create DVS Port Groups in vCenter

├── PG-Management  (VLAN 10)

├── PG-K8s-Nodes   (VLAN 20)

├── PG-Databases   (VLAN 30)

└── PG-Services    (VLAN 40)

Step 4:  Set Port Group security policies

└── K8s port group: Forged Transmits=Accept, MAC Changes=Accept

Step 5:  Create vSAN Storage Policies

├── Policy-DevQA     (FTT=0 — no redundancy for non-prod)

├── Policy-Prod      (FTT=1 RAID-1 — mirrored for prod)

└── Policy-Databases (RAID-5 — erasure coded for DB data)

Step 6:  Create VM folders in vCenter (organisation)

├── /Management

├── /K8s-Masters

├── /K8s-Workers

├── /Databases

└── /Services

Step 7:  Enable vSphere HA and DRS on cluster

├── HA: ON, admission control 25%

└── DRS: Fully Automated, threshold 3

Step 8:  Create DRS anti-affinity rules

└── K8s masters must run on different ESXi hosts (no single point of failure)

Step 9:  Verify NTP sync on all ESXi hosts

└── All hosts synced to same NTP source

## 4.2 Step 1 — Verify VxRail Health

Log in to VxRail Manager before anything else. Every node must show green.

# VxRail Manager URL:

https://vxrail-manager.internal.company.com

# Default admin: admin / VMware1! (change at first login)

# Also check via govc CLI from your workstation:

export GOVC_URL=https://vcenter.internal.company.com

export GOVC_USERNAME=administrator@vsphere.local

export GOVC_PASSWORD='YourPassword'

export GOVC_INSECURE=0

# Check all 6 ESXi hosts are connected

govc host.info '*' | grep -E "Name:|State:|Connection"

# Expected: Connection state: connected for all 6

# Check vSAN health and free space

govc datastore.info 'vsanDatastore' | grep -E "Free:|Capacity:"

# Expected: significant free space available

# Check existing VMs (note count — do not disrupt these)

govc find . -type m | wc -l

## 4.3 Step 2 — Configure Physical Switch VLANs

Before creating port groups in vCenter, the physical Top-of-Rack switch must have VLANs trunked on all VxRail node uplinks. The switch must also support LACP (bonded NICs) and jumbo frames (MTU 9000) for vSAN.

# Dell PowerSwitch OS10 syntax (adapt for your switch vendor):

# For each VxRail node uplink pair (6 nodes = 12 ports):

interface ethernet 1/1/1    # Node-1 vmnic0

description VxRail-Node1-vmnic0

no shutdown

switchport mode trunk

switchport trunk allowed vlan 10,20,30,40,80,90

flowcontrol receive off

mtu 9216

interface ethernet 1/1/2    # Node-1 vmnic1

description VxRail-Node1-vmnic1

no shutdown

switchport mode trunk

switchport trunk allowed vlan 10,20,30,40,80,90

mtu 9216

# LACP bond for both uplinks from Node-1

interface port-channel 1

description VxRail-Node1-Bond

no shutdown

switchport mode trunk

switchport trunk allowed vlan 10,20,30,40,80,90

mtu 9216

# Repeat for all 6 nodes using port-channels 1-6

# VLAN 80 = vSAN traffic, VLAN 90 = vMotion (these must be MTU 9000!)

NOTE:  CRITICAL: vSAN requires MTU 9000 (jumbo frames) on all switch ports connecting VxRail nodes. Without this, vSAN health checks will warn and performance degrades.

## 4.4 Step 3 — Create DVS Port Groups in vCenter

# Method 1: vCenter UI

#   vCenter → Networking → VxRail-DVS → Actions → Add Distributed Port Group

#   Name: PG-K8s-Nodes | VLAN ID: 20 | Ports: 128

#   Name: PG-Databases  | VLAN ID: 30 | Ports: 128

#   Name: PG-Services   | VLAN ID: 40 | Ports: 128

# Method 2: govc CLI (faster — scriptable)

export GOVC_URL=https://vcenter.internal.company.com

export GOVC_USERNAME=administrator@vsphere.local

export GOVC_PASSWORD="${VCENTER_PASSWORD}"

export GOVC_DATACENTER=Datacenter

DVS="VxRail-DVS"

for PG_SPEC in "PG-K8s-Nodes:20" "PG-Databases:30" "PG-Services:40"; do

PG_NAME=$(echo $PG_SPEC | cut -d: -f1)

VLAN_ID=$(echo $PG_SPEC  | cut -d: -f2)

govc dvs.portgroup.add     -dvs="${DVS}" -type=earlyBinding     -nports=128 -vlan="${VLAN_ID}" "${PG_NAME}"

echo "Created: $PG_NAME (VLAN $VLAN_ID)"

done

# Set security on K8s port group (MetalLB requires these):

# vCenter UI: PG-K8s-Nodes → Settings → Security → Edit

#   Promiscuous mode:    Reject   (default OK)

#   MAC address changes: Accept   ← REQUIRED for MetalLB

#   Forged transmits:    Accept   ← REQUIRED for MetalLB VIP advertisements

## 4.5 Step 5 — Create vSAN Storage Policies

# vCenter UI: Home → Policies and Profiles → VM Storage Policies → Create

Policy: Policy-DevQA

Rule set 1: vSAN

Failures to tolerate (FTT): 0

Failure tolerance method: No data redundancy

# Use for: Dev + QA VMs and PVs (saves space, no prod risk)

Policy: Policy-Production

Rule set 1: vSAN

Failures to tolerate (FTT): 1

Failure tolerance method: RAID-1 (Mirroring)

# Use for: Prod K8s workers, Prod app PVs

# Effect: 2 copies of every write across different hosts

Policy: Policy-Databases

Rule set 1: vSAN

Failures to tolerate (FTT): 1

Failure tolerance method: RAID-5 (Erasure coding)

# Use for: All database VM disks (PostgreSQL data files, MongoDB data)

# Effect: More space-efficient than RAID-1 (1.33x overhead vs 2x)

# Requires: Minimum 4 hosts (you have 6 — OK)

# 5. Oracle Linux 9 — Installation & VM Setup

All on-prem VMs run Oracle Linux 9 (OL9). This section covers creating the base OL9 template in vCenter, installing it, and configuring it correctly for use as K8s nodes, database servers, and service VMs.

NOTE:  Your environment uses Oracle Linux 9, NOT Ubuntu. Commands use dnf (not apt), firewalld (not ufw), nmcli (not netplan), and oracle@ SSH user (not ubuntu@).

## 5.1 OL9 vs Ubuntu — Quick Command Reference

| Task | Ubuntu Command | Oracle Linux 9 Command |
| --- | --- | --- |
| Install packages | apt install -y pkg | dnf install -y pkg |
| Update system | apt update && apt upgrade | dnf update -y |
| Add package repo | /etc/apt/sources.list.d/ | /etc/yum.repos.d/ |
| Firewall rule | ufw allow 6443/tcp | firewall-cmd --permanent --add-port=6443/tcp && firewall-cmd --reload |
| Firewall status | ufw status | firewall-cmd --list-all |
| Network config | /etc/netplan/*.yaml | nmcli / /etc/sysconfig/network-scripts/ |
| Package lock | apt-mark hold pkg | dnf versionlock add pkg |
| SSH user | ubuntu@host | oracle@host |
| vSphere guest type | ubuntu64Guest | oracleLinux9_64Guest |
| SELinux/AppArmor | AppArmor (not enforced) | SELinux (enforcing by default) |
| Service manager | systemctl (same) | systemctl (same) |
| NIC name (VMware) | ens192 (same) | ens192 (VMXNET3) |

## 5.2 Download Oracle Linux 9 ISO and Upload to vSAN

# From your jump host or workstation:

# Download Oracle Linux 9.4 ISO (Minimal — ~1 GB, no GUI)

wget https://yum.oracle.com/ISOS/OracleLinux/OL9/u4/x86_64/OracleLinux-R9-U4-x86_64-boot.iso \

-O /tmp/OracleLinux-9.4-x86_64.iso

# Upload ISO to vSAN datastore (so all ESXi hosts can access it)

govc datastore.mkdir -ds=vsanDatastore iso

govc datastore.upload \

-ds=vsanDatastore \

/tmp/OracleLinux-9.4-x86_64.iso \

iso/OracleLinux-9.4-x86_64.iso

# Verify upload

govc datastore.ls -ds=vsanDatastore iso/

## 5.3 Create Base VM in vCenter

# Create the base VM that will become our OL9 template

govc vm.create \

-c=4 \                          # 4 vCPUs

-m=8192 \                       # 8 GB RAM

-disk=60GB \                    # 60 GB disk

-net="PG-K8s-Nodes" \           # Network port group

-g=oracleLinux9_64Guest \       # ← IMPORTANT: Oracle Linux guest type

-ds=vsanDatastore \

-on=false \

ol9-base-template

# Set disk UUID (REQUIRED for vSphere CSI storage driver)

govc vm.change -vm=ol9-base-template -e disk.EnableUUID=TRUE

# Attach ISO for OS installation

govc vm.cdrom.insert \

-vm=ol9-base-template \

-device="CD/DVD drive 1" \

"vsanDatastore/iso/OracleLinux-9.4-x86_64.iso"

# Power on — open vCenter console to complete installation

govc vm.power -on ol9-base-template

# Open console URL:

echo "Open vCenter console: https://vcenter.internal.company.com/ui"

echo "Navigate to: ol9-base-template → Launch Web Console"

## 5.4 Oracle Linux 9 Installation Steps (via vCenter Console)

Complete the Anaconda graphical installer with these settings:

| Setting | Value | Notes |
| --- | --- | --- |
| Language | English (United States) | Default OK |
| Time & Date | Your timezone (e.g. Asia/Kolkata) | NTP will be configured later |
| Software Selection | Minimal Install | NO GUI — smaller and more secure |
| Network & Hostname | Enable ens192, set temp IP 10.0.1.200/24 | Permanent IPs set via cloud-init |
| Gateway | 10.0.1.1 | Your management subnet gateway |
| DNS | 10.0.1.5 | Your on-prem DNS server (set up in Step 6) |
| Hostname | ol9-template | Will be changed per-VM after clone |
| Root Password | DISABLE root login | Use sudo from oracle user only |
| User Creation | oracle / TemplatePass2026! (admin: Yes) | This user SSHs to all VMs |
| Installation Disk | Select vSAN disk, Automatic partitioning | Let installer partition |
| Begin Install | Click Begin Installation, then Reboot | — |

## 5.5 Post-Install Template Configuration (Run Once on Base VM)

# SSH to the base VM after installation

ssh oracle@10.0.1.200

# ── 1. Enable Oracle Linux repositories ──────────────────────────────

sudo dnf install -y oracle-epel-release-el9

sudo dnf config-manager --enable ol9_baseos_latest ol9_appstream ol9_UEKR7

# ── 2. Full system update ─────────────────────────────────────────────

sudo dnf update -y

# ── 3. Install baseline tools ─────────────────────────────────────────

sudo dnf install -y \

curl wget vim htop net-tools bind-utils \

nfs-utils chrony open-vm-tools \

cloud-init cloud-utils-growpart \

python3 bash-completion \

socat conntrack-tools ipset ipvsadm \

tar gzip unzip git

# ── 4. Enable and start open-vm-tools (VMware guest agent) ───────────

sudo systemctl enable --now vmtoolsd

# ── 5. Configure SSH (harden) ─────────────────────────────────────────

sudo sed -i 's/#PermitRootLogin.*/PermitRootLogin no/' /etc/ssh/sshd_config

sudo sed -i 's/#PasswordAuthentication.*/PasswordAuthentication no/' /etc/ssh/sshd_config

# Add your team SSH public keys:

mkdir -p ~/.ssh && chmod 700 ~/.ssh

echo "YOUR_TEAM_PUBLIC_KEY_HERE" >> ~/.ssh/authorized_keys

chmod 600 ~/.ssh/authorized_keys

sudo systemctl restart sshd

# ── 6. NTP / chrony (time sync) ───────────────────────────────────────

sudo tee /etc/chrony.conf << 'CHRONY'

server ntp.internal.company.com iburst

driftfile /var/lib/chrony/drift

makestep 1.0 3

rtcsync

CHRONY

sudo systemctl enable --now chronyd

chronyc tracking

# ── 7. Set SELinux to Permissive for K8s nodes ────────────────────────

# (Required for Kubernetes — enforcing mode blocks container operations)

sudo sed -i 's/^SELINUX=enforcing/SELINUX=permissive/' /etc/selinux/config

sudo setenforce 0   # immediate effect without reboot

# ── 8. Disable swap (REQUIRED for Kubernetes) ─────────────────────────

sudo swapoff -a

sudo sed -i '/ swap / s/^\(.*\)$/#/g' /etc/fstab

# ── 9. Disable cloud-init (re-enable when converting to template) ─────

sudo touch /etc/cloud/cloud-init.disabled

# ── 10. Clean up for template ─────────────────────────────────────────

sudo dnf clean all

sudo rm -f /etc/ssh/ssh_host_*      # regenerated on first boot

sudo truncate -s0 /etc/machine-id   # reset machine ID

sudo rm -f /var/lib/dbus/machine-id

sudo cloud-init clean --logs

sudo poweroff

## 5.6 Convert VM to Template in vCenter

# After VM powers off after cleanup above:

# Method 1: vCenter UI

#   Right-click ol9-base-template → Template → Convert to Template

# Method 2: govc CLI

govc vm.markastemplate ol9-base-template

# Verify:

govc find . -type m -name "ol9-base-template"

# Should show type = VirtualMachineTemplate

## 5.7 Clone VMs from Template (All 27 VMs)

#!/bin/bash

# Clone all required VMs from the OL9 template

# Run from jump host with govc configured

TEMPLATE="ol9-base-template"

DATASTORE="vsanDatastore"

DATACENTER="Datacenter"

# VM list: name, IP, port-group, vCPU, RAM(MB), folder

declare -A VMS=(

# Management VMs

["mgmt-jump-01"]="10.0.1.20:PG-Management:2:4096:Management"

["mgmt-dns-01"]="10.0.1.5:PG-Management:2:4096:Management"

# K8s Control Plane

["k8s-master-1"]="10.0.3.11:PG-K8s-Nodes:4:8192:K8s-Masters"

["k8s-master-2"]="10.0.3.12:PG-K8s-Nodes:4:8192:K8s-Masters"

["k8s-master-3"]="10.0.3.13:PG-K8s-Nodes:4:8192:K8s-Masters"

# K8s Workers

["k8s-worker-1"]="10.0.4.21:PG-K8s-Nodes:8:16384:K8s-Workers"

["k8s-worker-2"]="10.0.4.22:PG-K8s-Nodes:8:16384:K8s-Workers"

["k8s-worker-3"]="10.0.4.23:PG-K8s-Nodes:8:16384:K8s-Workers"

["k8s-worker-4"]="10.0.4.24:PG-K8s-Nodes:8:16384:K8s-Workers"

["k8s-worker-5"]="10.0.4.25:PG-K8s-Nodes:8:16384:K8s-Workers"

["k8s-worker-6"]="10.0.4.26:PG-K8s-Nodes:8:16384:K8s-Workers"

# Databases

["pg-dev-01"]="10.0.5.11:PG-Databases:4:8192:Databases"

["pg-qa-01"]="10.0.5.12:PG-Databases:4:8192:Databases"

["mongo-dev-01"]="10.0.5.14:PG-Databases:4:8192:Databases"

# Services

["svc-harbor-01"]="10.0.6.11:PG-Services:4:8192:Services"

["svc-minio-01"]="10.0.6.12:PG-Services:4:8192:Services"

["svc-mon-01"]="10.0.6.13:PG-Services:4:8192:Services"

)

for VM_NAME in "${!VMS[@]}"; do

IFS=':' read -r IP PG VCPU RAM FOLDER <<< "${VMS[$VM_NAME]}"

echo "Cloning $VM_NAME (IP: $IP) ..."

govc vm.clone \

-vm="${TEMPLATE}" \

-on=false \

-ds="${DATASTORE}" \

-folder="${FOLDER}" \

"${VM_NAME}"

# Set resources

govc vm.change -vm="${VM_NAME}" -c="${VCPU}" -m="${RAM}"

govc vm.change -vm="${VM_NAME}" -e disk.EnableUUID=TRUE

echo "  Created: $VM_NAME"

done

echo "All VMs created. Configure IPs via cloud-init before powering on."

# 6. Network Setup

Network setup happens at two layers: (1) Physical switch VLAN configuration (Section 4.3 above), and (2) Operating system level IP/firewall on each OL9 VM.

## 6.1 IP Address Plan

| Subnet | VLAN | Purpose | Key IPs |
| --- | --- | --- | --- |
| 10.0.1.0/24 | VLAN 10 | Management | vCenter (10.0.1.10), DNS (10.0.1.5), Veeam (10.0.1.40), Jump host (10.0.1.20) |
| 10.0.3.0/24 | VLAN 20 | K8s Control Plane | masters: 10.0.3.11-13, API VIP: 10.0.3.100 |
| 10.0.4.0/24 | VLAN 20 | K8s Workers | workers: 10.0.4.21-26, MetalLB pool: 10.0.4.200-220 |
| 10.0.5.0/24 | VLAN 30 | Databases | PostgreSQL: 10.0.5.11-23, MongoDB: 10.0.5.14-26 |
| 10.0.6.0/24 | VLAN 40 | Services | Harbor: 10.0.6.11, MinIO: 10.0.6.12, Monitoring: 10.0.6.13 |
| 192.168.0.0/16 | Internal | K8s Pod CIDR | Calico allocates pod IPs from this range |
| 10.96.0.0/12 | Internal | K8s Service CIDR | ClusterIP service addresses |

## 6.2 Set Static IP on Each OL9 VM (nmcli)

# Set static IP on Oracle Linux 9 (nmcli — NOT netplan)

# Run on each VM after first boot, replacing IP/GW/DNS as needed

VM_IP="10.0.3.11"        # Change per VM

GATEWAY="10.0.3.1"       # Your subnet gateway

DNS="10.0.1.5"           # Your internal DNS server

# Get the connection name (usually "ens192" or similar)

nmcli connection show

# Set static IP (replace "ens192" with actual connection name)

nmcli connection modify ens192 \

ipv4.method manual \

ipv4.addresses "${VM_IP}/24" \

ipv4.gateway "${GATEWAY}" \

ipv4.dns "${DNS}" \

connection.autoconnect yes

# Apply immediately

nmcli connection up ens192

# Verify

ip addr show ens192

ping -c3 10.0.1.5       # Test DNS server reachability

## 6.3 Configure firewalld on K8s Nodes

# Run on ALL K8s masters and workers (Oracle Linux 9 — firewalld)

sudo systemctl enable --now firewalld

# Allow SSH from management subnet only

sudo firewall-cmd --permanent --add-rich-rule='rule family=ipv4 source address="10.0.1.0/24" port port=22 protocol=tcp accept'

# Kubernetes API server port

sudo firewall-cmd --permanent --add-port=6443/tcp

# etcd (control plane nodes only)

sudo firewall-cmd --permanent --add-port=2379-2380/tcp

# Kubelet API

sudo firewall-cmd --permanent --add-port=10250/tcp

# NodePort range (for services)

sudo firewall-cmd --permanent --add-port=30000-32767/tcp

# Calico CNI ports

sudo firewall-cmd --permanent --add-port=179/tcp    # BGP

sudo firewall-cmd --permanent --add-port=4789/udp   # VXLAN

sudo firewall-cmd --permanent --add-port=5473/tcp   # Typha

# MetalLB member communication

sudo firewall-cmd --permanent --add-port=7946/tcp

sudo firewall-cmd --permanent --add-port=7946/udp

# VRRP (keepalived VIP)

sudo firewall-cmd --permanent --add-rich-rule='rule protocol value="vrrp" accept'

# Allow all traffic within K8s subnets (pod-to-pod, service-to-service)

sudo firewall-cmd --permanent --add-rich-rule='rule family=ipv4 source address="10.0.3.0/24" accept'

sudo firewall-cmd --permanent --add-rich-rule='rule family=ipv4 source address="10.0.4.0/24" accept'

sudo firewall-cmd --permanent --add-rich-rule='rule family=ipv4 source address="192.168.0.0/16" accept'

sudo firewall-cmd --permanent --add-rich-rule='rule family=ipv4 source address="10.96.0.0/12" accept'

sudo firewall-cmd --reload

sudo firewall-cmd --list-all

# 7. Kubernetes Cluster Setup on VxRail

We deploy a 3-master HA Kubernetes cluster using kubeadm. The API server VIP is managed by keepalived. Storage is provided by vSphere CSI driver backed by vSAN.

## 7.1 K8s Cluster Architecture

KUBERNETES HA ARCHITECTURE ON VXRAIL

═══════════════════════════════════════════════════════════════════════

Client requests

│

▼

MetalLB (10.0.4.200-220) — Layer 2 ARP, external service IPs

│

▼

Nginx Ingress Controller (DaemonSet on workers)

│

▼

Kubernetes Services (ClusterIP 10.96.0.0/12)

│

▼

Pods (Calico network, 192.168.0.0/16)

┌──────────────────────────────────────────────────────────┐

│  API SERVER LOAD BALANCING                               │

│                                                          │

│  kubectl / kubelets                                      │

│       │                                                  │

│       ▼                                                  │

│  VIP: 10.0.3.100 (keepalived — floats on active master) │

│       │                                                  │

│  HAProxy (on each master — listens on 10.0.3.100:6443)  │

│       │                                                  │

│  ┌────┴────────────────────────────────┐                 │

│  │  master-1    master-2    master-3   │                 │

│  │ 10.0.3.11  10.0.3.12  10.0.3.13   │                 │

│  │  etcd        etcd        etcd      │ (3-node quorum) │

│  │  API srv     API srv     API srv   │                 │

│  └─────────────────────────────────────┘                 │

└──────────────────────────────────────────────────────────┘

Workers (one K8s node per environment):

├── worker-1/2  → namespace: dev, qa        (Dev/QA workloads)

├── worker-3/4  → namespace: preprod        (PreProd workloads)

└── worker-5/6  → namespace: prod           (Prod — dedicated, tainted)

Storage:

└── vSphere CSI → vSAN PersistentVolumes per namespace

## 7.2 Prepare All K8s Nodes (Pre-kubeadm)

#!/bin/bash

# Run on ALL K8s VMs (3 masters + 6 workers) before kubeadm

# SSH: oracle@<node-ip>

# 1. Disable swap (Kubernetes requirement)

sudo swapoff -a

sudo sed -i '/ swap / s/^\(.*\)$/#/g' /etc/fstab

# 2. Load kernel modules

sudo tee /etc/modules-load.d/k8s.conf << EOF

overlay

br_netfilter

EOF

sudo modprobe overlay

sudo modprobe br_netfilter

# 3. Kernel networking parameters

sudo tee /etc/sysctl.d/99-k8s.conf << EOF

net.bridge.bridge-nf-call-iptables  = 1

net.bridge.bridge-nf-call-ip6tables = 1

net.ipv4.ip_forward                 = 1

EOF

sudo sysctl --system

# 4. Install containerd (container runtime) — Oracle Linux 9

sudo dnf config-manager --add-repo https://download.docker.com/linux/centos/docker-ce.repo

sudo dnf install -y containerd.io

sudo mkdir -p /etc/containerd

containerd config default | sudo tee /etc/containerd/config.toml

sudo sed -i 's/SystemdCgroup = false/SystemdCgroup = true/' /etc/containerd/config.toml

sudo systemctl restart containerd && sudo systemctl enable containerd

# 5. Add Kubernetes 1.29 RPM repo (Oracle Linux 9)

sudo tee /etc/yum.repos.d/kubernetes.repo << 'EOF'

[kubernetes]

name=Kubernetes

baseurl=https://pkgs.k8s.io/core:/stable:/v1.29/rpm/

enabled=1

gpgcheck=1

gpgkey=https://pkgs.k8s.io/core:/stable:/v1.29/rpm/repodata/repomd.xml.key

exclude=kubelet kubeadm kubectl cri-tools kubernetes-cni

EOF

# 6. Install kubeadm, kubelet, kubectl 1.29

sudo dnf install -y --disableexcludes=kubernetes \

kubelet-1.29.0 kubeadm-1.29.0 kubectl-1.29.0

# 7. Lock K8s package versions (prevent accidental upgrades)

sudo dnf install -y 'dnf-command(versionlock)'

sudo dnf versionlock add kubelet kubeadm kubectl

# 8. Enable kubelet (starts after kubeadm init)

sudo systemctl enable kubelet

echo "Node ready for kubeadm."

## 7.3 Set Up keepalived VIP on All 3 Masters

# Install on all 3 masters

sudo dnf install -y keepalived haproxy

# ── keepalived config (master-1 — MASTER, higher priority) ──────────

# On master-2 and master-3: change STATE to BACKUP, priority to 100 and 99

sudo tee /etc/keepalived/keepalived.conf << 'EOF'

global_defs { router_id k8s-master-1 }

vrrp_script chk_haproxy {

script "killall -0 haproxy"

interval 2

weight   2

}

vrrp_instance K8S_VIP {

state     MASTER     # BACKUP on master-2 and master-3

interface ens192

virtual_router_id 51

priority  101        # 100 on master-2, 99 on master-3

advert_int 1

virtual_ipaddress { 10.0.3.100/24 }

track_script { chk_haproxy }

}

EOF

# ── HAProxy config (same on all 3 masters) ──────────────────────────

sudo tee /etc/haproxy/haproxy.cfg << 'EOF'

frontend k8s-api

bind 0.0.0.0:6443

mode tcp

option tcplog

default_backend k8s-masters

backend k8s-masters

mode tcp

balance roundrobin

option tcp-check

server master1 10.0.3.11:6443 check fall 3 rise 2

server master2 10.0.3.12:6443 check fall 3 rise 2

server master3 10.0.3.13:6443 check fall 3 rise 2

EOF

sudo systemctl enable --now keepalived haproxy

# Verify VIP is active on master-1:

ip addr show ens192 | grep 10.0.3.100   # Should show on master-1

## 7.4 kubeadm Cluster Initialisation (Run on master-1 Only)

# ── Run ONLY on master-1 ──────────────────────────────────────────────

sudo kubeadm init \

--control-plane-endpoint "10.0.3.100:6443" \

--upload-certs \

--pod-network-cidr=192.168.0.0/16 \

--service-cidr=10.96.0.0/12 \

--kubernetes-version=1.29.0

# Save the output — it contains join commands for other masters and workers!

# Set up kubectl for oracle user

mkdir -p $HOME/.kube

sudo cp /etc/kubernetes/admin.conf $HOME/.kube/config

sudo chown oracle:oracle $HOME/.kube/config

# Verify cluster is up

kubectl get nodes    # Should show master-1 in NotReady state (no CNI yet)

kubectl get pods -A  # All pods except CoreDNS pending (waiting for CNI)

## 7.5 Install Calico CNI

# Run on master-1 after kubeadm init

# Install Calico v3.27 (handles pod networking + NetworkPolicy)

kubectl create -f https://raw.githubusercontent.com/projectcalico/calico/v3.27.0/manifests/tigera-operator.yaml

cat << 'EOF' | kubectl apply -f -

apiVersion: operator.tigera.io/v1

kind: Installation

metadata:

name: default

spec:

calicoNetwork:

ipPools:

- blockSize: 26

cidr: 192.168.0.0/16

encapsulation: VXLANCrossSubnet

natOutgoing: Enabled

nodeSelector: all()

EOF

# Wait for Calico to be ready

kubectl wait --for=condition=Ready pods -l k8s-app=calico-node -n calico-system --timeout=300s

# Verify — all nodes should now show Ready

kubectl get nodes

## 7.6 Join Other Masters and Workers

# ── Join master-2 and master-3 (use command from kubeadm init output) ──

# Example (use YOUR actual token/cert-hash from kubeadm init output):

sudo kubeadm join 10.0.3.100:6443 \

--token <TOKEN> \

--discovery-token-ca-cert-hash sha256:<HASH> \

--control-plane \

--certificate-key <CERT_KEY>

# ── Join all 6 workers (use worker join command from kubeadm init output) ──

sudo kubeadm join 10.0.3.100:6443 \

--token <TOKEN> \

--discovery-token-ca-cert-hash sha256:<HASH>

# ── Label workers by environment ──────────────────────────────────────

kubectl label node k8s-worker-1 env=dev

kubectl label node k8s-worker-2 env=qa

kubectl label node k8s-worker-3 env=preprod

kubectl label node k8s-worker-4 env=preprod

kubectl label node k8s-worker-5 env=prod

kubectl label node k8s-worker-6 env=prod

# ── Taint Prod workers (prevent non-prod pods from landing there) ─────

kubectl taint node k8s-worker-5 env=prod:NoSchedule

kubectl taint node k8s-worker-6 env=prod:NoSchedule

# ── Create namespaces ─────────────────────────────────────────────────

kubectl create namespace dev

kubectl create namespace qa

kubectl create namespace preprod

kubectl create namespace prod

# ── Verify ───────────────────────────────────────────────────────────

kubectl get nodes -o wide    # All 9 nodes: Ready

kubectl get namespaces       # dev, qa, preprod, prod created

# 8. Storage Setup (vSAN + CSI)

## 8.1 Install vSphere CSI Driver

The vSphere CSI driver lets Kubernetes claim persistent storage from vSAN as PersistentVolumes.

# ── 1. Create vCenter credentials secret ─────────────────────────────

kubectl create namespace vmware-system-csi

kubectl create secret generic vsphere-config-secret \

--namespace=vmware-system-csi \

--from-literal=csi-vsphere.conf="$(cat << 'EOF'

[Global]

cluster-id = "vxrail-cluster-01"

[VirtualCenter "vcenter.internal.company.com"]

insecure-flag = "false"

user = "csi-user@vsphere.local"

password = "VsphereCSI2026!"

port = "443"

datacenters = "Datacenter"

EOF

)"

# ── 2. Install vSphere CSI v3.3.0 ─────────────────────────────────────

kubectl apply -f https://raw.githubusercontent.com/kubernetes-sigs/vsphere-csi-driver/v3.3.0/manifests/vanilla/vsphere-csi-driver.yaml

# ── 3. Create StorageClasses ───────────────────────────────────────────

cat << 'EOF' | kubectl apply -f -

---

apiVersion: storage.k8s.io/v1

kind: StorageClass

metadata:

name: vsan-dev-qa

annotations:

storageclass.kubernetes.io/is-default-class: "false"

provisioner: csi.vsphere.volume

parameters:

storagepolicyname: "Policy-DevQA"

reclaimPolicy: Delete

volumeBindingMode: WaitForFirstConsumer

---

apiVersion: storage.k8s.io/v1

kind: StorageClass

metadata:

name: vsan-production

provisioner: csi.vsphere.volume

parameters:

storagepolicyname: "Policy-Production"

reclaimPolicy: Retain

volumeBindingMode: WaitForFirstConsumer

---

apiVersion: storage.k8s.io/v1

kind: StorageClass

metadata:

name: vsan-databases

provisioner: csi.vsphere.volume

parameters:

storagepolicyname: "Policy-Databases"

reclaimPolicy: Retain

volumeBindingMode: WaitForFirstConsumer

EOF

kubectl get sc   # Verify all 3 StorageClasses appear

# 9. Veeam Backup Setup

Veeam Backup and Replication v12 runs on a dedicated Windows Server 2022 VM. It uses VMware API integration for agentless backup of all OL9 VMs.

## 9.1 Veeam Architecture on VxRail

VEEAM BACKUP ARCHITECTURE

═══════════════════════════════════════════════════════════════

vxrail-vbr-01 (10.0.1.40)  —  Windows Server 2022 VM on VxRail

├── Veeam B&R v12 Server

├── Veeam Proxy (Hotadd transport — reads vSAN directly)

└── Veeam Repository pointing to → NAS (NFS share)

Backup method: HotAdd Transport

├── VBR VM runs on SAME vSAN as the target VMs

├── vSphere API allows direct vSAN disk read (no network copy)

└── FASTEST method — reads directly from NVMe via VMware internals

Backup targets:

├── All OL9 VMs    — agentless via VMware VADP API

├── K8s workloads  — Kasten K10 (Kubernetes-aware: PVCs, Secrets, etc.)

└── Databases      — Pre-freeze scripts run before snapshot

Schedule:

├── Dev/QA VMs    — Daily at 1 AM, 7-day retention

├── PreProd VMs   — Daily at 2 AM, 14-day retention

├── Prod VMs      — Daily at 3 AM + Weekly Sunday, 30-day / 90-day retention

└── Database dumps — Independent of Veeam (pg_dump / mongodump scripts)

## 9.2 Pre/Post-Freeze Scripts (Consistent DB Backups)

# These scripts run inside each VM before/after Veeam snapshot

# Install on PostgreSQL VMs — /etc/veeam/pre-freeze.sh

#!/bin/bash

# PRE-FREEZE: quiesce PostgreSQL before Veeam snapshot

psql -U postgres -c "CHECKPOINT;"

psql -U postgres -c "SELECT pg_start_backup('veeam_snapshot', true);"

echo "PostgreSQL backup mode started" | logger -t veeam-prefreeze

# POST-FREEZE: /etc/veeam/post-thaw.sh

#!/bin/bash

psql -U postgres -c "SELECT pg_stop_backup();"

echo "PostgreSQL backup mode ended" | logger -t veeam-postthaw

# For MongoDB VMs:

# PRE-FREEZE:

mongosh --eval "db.adminCommand({ fsync: 1, lock: true })"

# POST-FREEZE:

mongosh --eval "db.adminCommand({ fsyncUnlock: 1 })"

# 10. Migration Execution

## 10.1 Database Migration Approach

| Environment | Method | Duration | Risk Level |
| --- | --- | --- | --- |
| Dev PostgreSQL | pg_dump on Azure → scp → pg_restore on-prem | 1-2 hours | Low — dev data |
| QA PostgreSQL | pg_dump → pg_restore | 1-2 hours | Low — QA data |
| PreProd PostgreSQL | pg_dump → pg_restore + verify | 2-4 hours | Medium |
| Prod PostgreSQL | pglogical LIVE replication (zero downtime) | 2-4 weeks setup, ~1 min cutover | CRITICAL — needs thorough testing |
| Dev/QA MongoDB | mongodump → scp → mongorestore | 1-2 hours each | Low |
| Prod MongoDB | mongodump → restore + oplog tailing for live sync | 2-4 weeks, ~5 min cutover | CRITICAL |

## 10.2 PostgreSQL Migration Steps

# ── STEP 1: Dump from Azure (run from jump host with Azure VPN active) ──

AZURE_PG_HOST="your-azure-pg.postgres.database.azure.com"

AZURE_PG_USER="pgadmin@your-azure-pg"

DB_NAME="appdb"

pg_dump \

-h "${AZURE_PG_HOST}" \

-U "${AZURE_PG_USER}" \

-d "${DB_NAME}" \

--format=custom \        # compressed, faster restore

--no-owner \             # IMPORTANT: Azure creates roles that don't exist on-prem

--no-privileges \

-f /tmp/${DB_NAME}-$(date +%Y%m%d).dump

echo "Dump size: $(du -sh /tmp/${DB_NAME}*.dump)"

# ── STEP 2: Transfer to on-prem ──────────────────────────────────────

scp /tmp/${DB_NAME}-*.dump oracle@10.0.5.11:/tmp/

# ── STEP 3: Restore on-prem (run on pg-dev-01) ───────────────────────

ssh oracle@10.0.5.11

# Create role and database first

sudo -u postgres psql << 'SQL'

CREATE ROLE dev_user WITH LOGIN PASSWORD 'DevPass2026!';

CREATE DATABASE appdb OWNER dev_user;

SQL

# Restore

sudo -u postgres pg_restore \

--no-owner \

--no-privileges \

--role=dev_user \

-d appdb \

/tmp/appdb-*.dump

# ── STEP 4: Verify data ───────────────────────────────────────────────

sudo -u postgres psql -d appdb -c "\dt"

sudo -u postgres psql -d appdb -c "SELECT count(*) FROM your_main_table;"

# Compare count with Azure source before declaring success

## 10.3 MongoDB Migration Steps

# ── STEP 1: Dump from Azure Cosmos DB (Mongo API) ────────────────────

COSMOS_CS="mongodb://user:pass@your-cosmos.mongo.cosmos.azure.com:10255/?ssl=true"

mongodump \

--uri="${COSMOS_CS}" \

--db=appdb \

--gzip \

--out=/tmp/mongodump-$(date +%Y%m%d)/

# ── STEP 2: Transfer to on-prem ──────────────────────────────────────

scp -r /tmp/mongodump-*/ oracle@10.0.5.14:/tmp/

# ── STEP 3: Restore to on-prem MongoDB 7.0 ───────────────────────────

ssh oracle@10.0.5.14

mongorestore \

--host=localhost:27017 \

--authenticationDatabase=admin \

-u mongoAdmin \

-p 'MongoAdmin2026!' \

--gzip \

--db=appdb \

/tmp/mongodump-*/appdb/

# ── STEP 4: Verify ───────────────────────────────────────────────────

mongosh --eval "use appdb; db.stats()"

mongosh --eval "use appdb; db.your_collection.count()"

# Compare with Azure source count

## 10.4 Deploy Applications via ArgoCD

# ArgoCD reads your Git repo and deploys manifests to K8s

# 1. Install ArgoCD in K8s cluster

kubectl create namespace argocd

kubectl apply -n argocd -f \

https://raw.githubusercontent.com/argoproj/argo-cd/stable/manifests/install.yaml

# 2. Get initial admin password

kubectl -n argocd get secret argocd-initial-admin-secret \

-o jsonpath="{.data.password}" | base64 -d

# 3. Point ArgoCD at your Git repo (example for dev environment)

argocd app create dev-app \

--repo https://your-git-repo/app.git \

--path manifests/dev \

--dest-server https://kubernetes.default.svc \

--dest-namespace dev \

--sync-policy automated \

--auto-prune \

--self-heal

# 4. Sync (deploy)

argocd app sync dev-app

# 5. Check status

argocd app get dev-app

kubectl get pods -n dev

# 11. Migration Timeline — 32 Weeks

The 32-week timeline includes realistic buffers for hardware procurement lead times, approval processes, training, error recovery, and hypercare.

| Week(s) | Stage | Activity |
| --- | --- | --- |
| 1-2 | 0 — Discovery | Audit Azure, audit VxRail, read architecture docs, identify gaps |
| 3-4 | 0 — Procurement | RAISE ORDERS: switches, NAS, VPN appliance. Start approval process (CR) |
| 5-6 | 1 — Hardware Wait | Hardware lead time buffer. Meanwhile: plan DNS/VLAN/IP schema |
| 7-8 | 1 — Foundation Setup | Switches racked + configured. DNS/NTP/CA/VPN/jump host set up on VxRail |
| 9 | 2 — OL9 Template | Create Oracle Linux 9 VM template, configure, convert to template |
| 10 | 2 — VM Provisioning | Clone all 27 VMs from template, assign IPs, configure firewalld |
| 11 | 2 — K8s + Storage | kubeadm HA cluster, Calico, MetalLB, vSphere CSI, StorageClasses |
| 12 | 2 — Services + Buffer | Harbor, ArgoCD, Prometheus, Veeam. Error fix buffer week |
| 13-14 | 3 — Dev Migration | Migrate Dev PostgreSQL and MongoDB. Deploy Dev apps to K8s |
| 15-16 | 3 — Dev Validation | Dev team tests all functions. Sign-off required before QA |
| 17-18 | 3 — QA Migration | Migrate QA databases. Deploy QA apps. QA team testing |
| 19-20 | 3 — QA Validation | QA sign-off. Phase 1 cutover (DNS switch for Dev + QA) |
| 21-22 | 4 — PreProd Prep | Set up Patroni HA for PreProd PostgreSQL. pglogical setup starts |
| 23-24 | 4 — PreProd Migration | PreProd DB migration. Deploy PreProd apps. Performance testing |
| 25 | 4 — PreProd Buffer | Error fix + retest week. Performance comparison vs Azure |
| 26-27 | 4 — Prod Prep | pglogical LIVE replication from Azure Prod PostgreSQL to on-prem |
| 28 | 4 — Prod Cutover | Maintenance window: DNS cutover for Prod. Critical monitoring 72h |
| 29 | 4 — Azure Decommission | Decommission Azure resources (Dev/QA/PreProd). Validate cost savings |
| 30 | 4 — Final Prod | Prod fully stable. Decommission Azure Prod after verification |
| 31-32 | 5 — Hypercare | Intensive monitoring, fix any remaining issues, team handover |

## 11.1 Approval Gates

| Gate | Week | Name | Criteria |
| --- | --- | --- | --- |
| Gate 1 | Week 4 | Procurement Approval | Management sign-off on procurement spend + project kick-off |
| Gate 2 | Week 8 | Foundation Readiness | All foundation services healthy before any VM provisioning |
| Gate 3 | Week 12 | Infrastructure Readiness | K8s cluster, Veeam, Harbor, ArgoCD all verified working |
| Gate 4 | Week 16 | Dev Sign-off | Dev team confirms all functions work on on-prem before QA migration |
| Gate 5 | Week 20 | Phase 1 Sign-off | Both Dev and QA validated — go/no-go for Phase 2 |
| Gate 6 | Week 25 | PreProd Sign-off | Performance and function parity confirmed vs Azure PreProd |
| Gate 7 | Week 28 | Prod Cutover Approval | FINAL go/no-go — all stakeholders must approve Prod cutover |

# 12. Patching Cycles

| Frequency | What | How | Precautions |
| --- | --- | --- | --- |
| Monthly | OS Security Patches | All OL9 VMs — dnf update --security -y | Rolling: K8s drain → patch → uncordon. Databases: standby first |
| Quarterly | Full OS Update | All VMs — dnf update -y (all packages) | Full snapshot before. Schedule maintenance window |
| Quarterly | Kubernetes Minor Update | Upgrade K8s 1.29.x → 1.29.y | Masters first (one at a time), then workers |
| Semi-Annual | VxRail/ESXi Update | VxRail Manager → Upgrade → rolling host update | ONLY via VxRail Manager — NEVER patch ESXi directly with vSphere LCM |
| Semi-Annual | VMware vCenter Update | VAMI (vCenter Appliance Management) | Schedule: vCenter is HA-aware, but brief downtime possible |
| Annual | K8s Major Version | e.g., 1.29 → 1.30 (skip max 2 minor versions) | Full cluster backup + DR plan. Test in Dev first |
| Annual | PostgreSQL Major | pg_upgrade 15 → 16 (when ready) | Dump/restore or pg_upgrade in-place. Test on Dev first |

NOTE:  NEVER patch VxRail ESXi directly using vSphere Lifecycle Manager. Always use VxRail Manager to update ESXi. VxRail Manager coordinates firmware + ESXi together to prevent compatibility issues.

# 13. Common Errors and Solutions

## 13.1 VMware / vSphere Errors

Error: vSAN health warning: "Disk group degraded"

Cause: One host has a failed NVMe disk or a host is in maintenance mode.

Fix: Check VxRail Manager → Disk Groups. Replace failed disk (Dell support) or remove host from maintenance.

Error: VM fails to power on: "No compatible host"

Cause: DRS could not place VM due to resource constraints or anti-affinity rules.

Fix: Check cluster CPU/RAM utilisation. Adjust anti-affinity rules or increase DRS aggressiveness.

Error: vSphere CSI error: "failed to create volume"

Cause: CSI credentials wrong, or StoragePolicy name mismatch.

Fix: Check vsphere-config-secret. Verify policy name matches exactly what is in vCenter. Restart CSI pods.

Error: disk.EnableUUID=TRUE not set

Cause: vSphere CSI cannot attach volumes — required setting missing.

Fix: Set via govc: govc vm.change -vm=<vm> -e disk.EnableUUID=TRUE. Applies without reboot.

## 13.2 Kubernetes Errors

Error: Node stuck in NotReady

Cause: CNI (Calico) not installed or CrashLooping.

Fix: kubectl describe node <node>. Check calico pods: kubectl get pods -n calico-system. Reinstall Calico if needed.

Error: MetalLB VIP not responding

Cause: Port group security policy blocking gratuitous ARP.

Fix: In vCenter: PG-K8s-Nodes → Security → set Forged Transmits=Accept and MAC Changes=Accept.

Error: Pods in Pending state

Cause: No matching node (taint/toleration mismatch) or PVC not binding.

Fix: kubectl describe pod <pod>. Check node labels and taints: kubectl get nodes --show-labels.

Error: kubeadm init fails: "port 6443 is in use"

Cause: Previous kubeadm attempt left stale processes.

Fix: sudo kubeadm reset -f; sudo systemctl stop haproxy keepalived; retry kubeadm init.

## 13.3 Database Migration Errors

Error: pg_restore: "role does not exist"

Cause: Azure PostgreSQL creates roles matching the Azure login name. These do not exist on-prem.

Fix: Use --no-owner --no-privileges --role=dev_user in pg_restore command.

Error: MongoDB restore error: "namespace not found"

Cause: Target MongoDB version mismatch or auth issue.

Fix: Verify: mongosh --version should be 7.0+. Check auth: use admin; db.auth("user","pass").

Error: pglogical replication lag

Cause: Network bandwidth insufficient or long-running transactions blocking replication slot.

Fix: Monitor: SELECT * FROM pg_replication_slots; Check lag with SELECT now() - pg_last_xact_replay_timestamp();

# 14. Team Responsibilities

| Role | Responsibilities |
| --- | --- |
| Infrastructure Lead | VxRail, vCenter, vSAN, switches, Veeam, OL9 VMs, firewall, patching |
| Platform/K8s Engineer | kubeadm, Calico, MetalLB, vSphere CSI, ArgoCD, Harbor, StorageClasses |
| Database Administrator | PostgreSQL migration (pg_dump/pglogical), MongoDB migration, Patroni HA |
| Application Dev Lead | App manifests for K8s, image builds, ArgoCD app definitions, smoke tests |
| DevOps/CI-CD Engineer | Pipeline changes (point to on-prem Harbor + ArgoCD), secret migration |
| QA Lead | Testing on Dev and QA environments, sign-off at Gate 4 and Gate 5 |
| Project Manager | Timeline tracking, approval gates, stakeholder communication, risk register |
| Security/Compliance | TLS certificates, RBAC review, NetworkPolicy, secret management, audit |

# 15. Open Items / Review Notes

Please add your questions, suggestions, and concerns below. This section is for team review comments.

| # | Item | Owner | Status |
| --- | --- | --- | --- |
| 1 | Confirm actual VxRail node specs (CPU, RAM, NVMe capacity) | Infrastructure Lead | Open |
| 2 | Confirm existing switch supports VLAN trunking + LACP + MTU 9000 | Infrastructure Lead | Open |
| 3 | Do we have an existing NAS for backups or need to procure? | Infrastructure Lead | Open |
| 4 | Confirm Veeam B&R v12 licence is available | Infrastructure Lead | Open |
| 5 | Confirm Azure VPN Gateway to be set up or ExpressRoute available? | Infrastructure Lead | Open |
| 6 | Do we use internal CA (step-ca) or buy wildcard TLS cert? | Security/Compliance | Open |
| 7 | Confirm actual Azure PostgreSQL and MongoDB database sizes | DBA | Open |
| 8 | Confirm application supports MongoDB 7.0 wire compatibility | App Dev Lead | Open |
| 9 | Confirm pglogical licence / extension available on Azure PostgreSQL Flexible Server | DBA | Open |
| 10 | Agree on maintenance window timing for Prod cutover (Gate 7) | PM + All | Open |

ADD YOUR SUGGESTIONS OR CONCERNS BELOW:

1. _______________________________________________________________________________________

2. _______________________________________________________________________________________

3. _______________________________________________________________________________________

4. _______________________________________________________________________________________

5. _______________________________________________________________________________________

6. _______________________________________________________________________________________

7. _______________________________________________________________________________________

8. _______________________________________________________________________________________

# 16. Detailed Reference — Repository Files

Full step-by-step guides are in the GitHub repository. This document summarises the plan. For exact commands and configs, refer to these files:

| File | Contents |
| --- | --- |
| 00-Index.md | Master navigation, complete 32-week timeline, VM allocation table, IP plan |
| 01-Architecture-Overview.md | Full Azure architecture, full VxRail architecture, target state, procurement decision tree |
| 02-Current-Infra-Inventory.md | Scripts to audit your VxRail cluster hardware capacity |
| 03-Procurement-Guide.md | What to order, pricing, lead times, software licences |
| 04-Initial-Setup-Before-Migration.md | 15-step foundation: DNS, NTP, CA, VPN, Ansible, jump host |
| 05-Infrastructure-Assessment.md | vSphere capacity audit, cluster readiness checklist |
| 06-Oracle-Linux-VMs.md | OL9 template creation, dnf commands, cloud-init, SELinux/firewalld |
| 07-VM-Provisioning-vSphere.md | govc scripts to create all 27 VMs, anti-affinity rules |
| 08-Network-vSphere.md | DVS port groups, MetalLB, keepalived, firewalld rules |
| 09-Storage-vSAN.md | vSAN storage policies, vSphere CSI driver, StorageClasses, MinIO |
| 10-Kubernetes-vSphere.md | kubeadm HA, Calico, MetalLB, vSphere CCM, full verification |
| 11-Veeam-Backup.md | Veeam B&R v12 setup, VM jobs, Kasten K10, restore procedures |
| 12-Migration-Execution.md | Master migration commands: Harbor, ArgoCD, PostgreSQL, MongoDB, DNS |
| 13-Phase1-Dev-QA.md | Phase 1 week-by-week: Dev + QA infrastructure, DB migration, validation |
| 14-Phase2-PreProd-Prod.md | Phase 2: Patroni HA, pglogical live replication, prod cutover |
| 15-Cutover-Runbook.md | DNS cutover script, smoke tests, rollback tree, 72h monitoring checklist |
| 16-Patching-Cycles.md | Monthly/quarterly/semi-annual/annual patch runbooks |
| 17-Troubleshooting-Errors.md | Error catalog: 12 categories, every common error with fix |

Repository: https://github.com/Shasi19/Migration

Primary directory: docs/VxRail-VMware-Migration/