# On-Premises Dell VxRail TCO and Operations - V3

Prepared 2026-09-09 | Full new-cluster purchase model

EXECUTIVE DECISION

If a new six-node Dell VxRail cluster must be purchased, on-premises is not automatically cheaper than the current Azure bill. Budget $1.04M-$2.39M initially, $390k-$980k annually, and $2.39M-$5.75M over three years including migration. With a new purchase, Azure is the best immediate financial and operational choice.

FULL ACQUISITION BUDGET

Six VxRail nodes: $600k-$1.2M. VMware/vSphere licensing: $150k-$400k. TOR switching/optics: $50k-$120k. Backup repository: $25k-$80k. Firewall/VPN/load balancing: $30k-$100k. Rack/UPS/PDUs/power: $50k-$150k. Commissioning/spares: $40k-$120k. Initial subtotal: $945k-$2.17M. Approval envelope with 10% contingency: $1.04M-$2.39M.

ANNUAL OPERATING COST

Hardware support: $60k-$150k. VMware support: $50k-$150k. Power/cooling: $35k-$90k. Backup/offsite DR: $25k-$75k. OS/security/platform support: $25k-$75k. Operations staffing: $180k-$400k. Refresh reserve: $15k-$40k. Fully loaded annual total: $390k-$980k.

OPERATIONAL EFFORT

Monthly OS patching: 3-6 engineer-days. Kubernetes upgrades: 5-10 engineer-days per quarter. VxRail/vSphere lifecycle: 3-8 engineer-days per maintenance window. Database patching, failover, backup checks, restore tests, certificate rotation, vulnerability remediation, capacity reviews, incidents, and on-call coverage are continuous responsibilities. Two FTE is a minimum shared model; 3-4 FTE is more realistic for 24x7 production ownership.

MIGRATION EFFORT

Discovery/design: $25k-$50k. Platform/network build: $45k-$100k. QA: $20k-$45k. PREPROD: $30k-$65k. PROD replication/canary/cutover/hypercare: $50k-$120k. Governance/security: $10k-$40k. Total: $180k-$420k over 20-28 weeks.

THREE-YEAR GRAPH DATA

Azure: $0.86M | VxRail low: $2.39M | VxRail high: $5.75M. Color chart: Azure blue, VxRail low amber, VxRail high red. Visual charts are included in docs/Azure-VxRail-VMware-Migration/assets/onprem-tco-bars.svg and onprem-operating-model.svg.

FINAL RECOMMENDATION

Remain on Azure and optimize first. Approve a new VxRail purchase only after Dell/Broadcom quotes, facilities capacity, 2-4 FTE ownership, memory headroom, database compatibility, immutable offsite DR, and complete three-year TCO approval.